## Sayfa1
Resource Name | Resource Type | Role & Responsibility | Weekly Effort (Hours) | Total Duration (14 Weeks)
Zehra Berre Akyüz | Human Resource | Project Manager | 3 Hours | 42 Hours
Tuba Eraslan | Human Resource | Backend Lead | 4 Hours | 56 Hours
Ceren Şengül | Human Resource | Frontend Lead | 4 Hours | 56 Hours
Can Tasar | Human Resource | QA & Documentation | 3 Hours | 42 Hours
Jira / GitHub | Software | Project Tracking & Hosting | - | Free Tier
PC & Internet | Infrastructure | Development Environment | - | Existing
Phase | Tasks | Timeline
Phase 1: Initiation | Project Definition, Role Allocation, and Jira Setup | Week 1 - 2
Phase 2: Analysis | Requirement Analysis and UML Diagram Design | Week 3 - 4
Phase 3: Design | Database Schema and UI/UX Mockup Design | Week 5 - 6
Phase 4: Development | Backend API and Frontend Integration | Week 7 - 10
Phase 5: Testing | Quality Assurance (QA) and Bug Fixing | Week 11 - 12
Phase 6: Delivery | GitHub Upload and Final Project Presentation | Week 13 - 14
Project Overview
Project Name: StockWise – Smart Inventory Tracking System
Problem: Manual inventory management leads to errors, stockouts, and financial loss.
Solution: A web-based, automated platform for real-time stock monitoring and reporting.
Target Users: Small to medium-sized businesses, warehouse managers, and retail stores.